## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 1 | 2 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Students' Success Equation: cracking the variables |  | Project Id: | IAC IP23 | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 1 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 1 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2024-11-29 | Project Team Lead: | ABC |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 5 |  |  |  |  | 5
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Challenges in obtaining accurate academic data | Can lead to inaccurate analysis and conclusions | Establish effective communication with educational institutions and verify data through cross-referencing. | Data Analyst | High |  | Open
2 | Risk | Low intern participation in events | May distort the representation of event participation | Implement incentives to encourage intern involvement and ensure clear communication about events. | Project Manager | Moderate |  | Open
3 | Risk | Limited availability of intern career aspiration data | Hinders the analysis of career aspirations | Conduct surveys or interviews to gather accurate career aspiration data and create a supportive environment for open communication. | Data Analyst | Moderate |  | Open
5 | Issue | Insufficient resources for in-depth data analysis | Limits the depth and scope of analysis | Prioritize data sources, focus on key metrics, and consider seeking additional resources or expertise. | Data Analyst | Moderate |  | Open
6 | Dependancy | Access to intern data from educational institutions | Essential for completing the analysis | Maintain open communication with educational institutions and establish clear protocols for data sharing and access. | Project Manager | High |  | Open
7 | Assumption | Availability of reliable academic performance data | Improves the accuracy of analysis | Cross-reference data from various sources to ensure accuracy and establish protocols for data validation and verification. | Data Analyst | High |  | Open | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24